## How to use this template
How to use this template
Template last updated: |  | 2024-03-01
This document includes the three following tabs:
Title | Description
Guidance | A high-level description of how to fill in the risk register
Risk register template | A blank template risk register for you to fill in
Risk register example | A risk register completed with three examples

## Guidance
Guidance
Identifying, monitoring, and managing risk is a key part of good charity governance and Trustees must develop and maintain a risk register. A risk is something that may or may not happen. If it does happen, it could affect your Group, District or County/Area/Region (Scotland). An issue is when you’re dealing with something that’s already happened. For example, you may identify there’s a risk of damage to your Scout meeting place in bad weather. If that happens, you’ll need to consider how urgently repairs are needed, or whether you need to cancel sessions to keep everyone safe. Simply thinking it through is risk management. A risk register is a tool to help you record your risks and identify what to focus on. It’ll help you to manage risks and make the right decisions. Trustees develop and maintain the risk register, and put controls in place. But, they can delegate actions to others. For example, the Trustee Board might decide a building needs maintenance, but they’re not responsible for doing the repairs themselves. The Risk Register is designed to support Trustee Boards to focus on risks to the charity. It prompts Trustee Boards to follow guidance from charity regulators on key areas of risk. This is distinct from guidance on Risk Assessments required for all Scouts activities and premises. To find out about the Trustees responsibilities for risk assessments read the Safety Checklist. |  |  |  | Further information
Charities and risk management CC26
Checklist of financial controls for charities
How to manage risk NCVO
Safety checklist
Step 1: Identify the risks | Step 2: Assess the risks |  |  | Step 3: Control the risk | Step 4: Monitor the risk
Work with other Trustees and Leadership teams to identify risks. The risks you identify will depend on the size of your Group, District or County. The risk categories you should consider: 1. External – Risks which may affect the Group/ District/ County, such as changes in the external environment (that we can’t really control). 2. Operational – Risks that occur from the activities we carry out. 3. Financial – Financial risks in terms of funding and planning. 4. Legal and Regulatory – Risks related to complying with legislation and regulations. 5. Governance – Risks that are part of the effective and ethical management of the Group/ District/County. 6. Data Protection – Risks to personal or organisation data that could result in loss, damage, misuse, or destruction. | You need to understand the impact and likelihood of the risks you’ve identified. We use a 4x4 grid to help us work out the score of a particular risk. Trying to decide on an appropriate score is difficult if you’re making the judgment on your own. It’s always best to review risks and their scores as a team. That way, you have a more balanced, accurate view of each risk. Check the definitions for impact and likelihood below to help you. Working out the overall risk score In this template, the overall risk score is worked out by multiplying impact by likelihood, and adding the impact score again. (Impact x likelihood) + impact = risk score |  |  | To begin with, think about what the score would be before you do anything about the risk. This is your pre-control score. Then, think about all the different things that help you to manage that risk, by either reducing its impact or the likelihood of it happening. These are your controls. Once you’ve recorded all the controls you have in place, think about how much that’s reduced the score you started with. This is your post-control score. Think of this as the 'real' level of risk. Are there any other things you can do (perhaps longer-term plans) to reduce the impact or likelihood even further? Please write these up in your ‘Further planned actions’ column. | Make sure every risk has a named 'owner' and named people who are 'responsible' for any necessary actions. Remember, tasks can be delegated to people outside the Trustee Board. It's important they provide regular updates on these actions, so you know if the risk is being managed correctly. Here are a few ways you can monitor risks: - Ask for reports and updates on actions - Review risks at Board meetings - Review risk assessments
Impact score
| Score | Description | Example
| 1 | Minor | No impact on activities or reputation Complaint unlikely Legal action unlikely
| 2 | Important | Some activity disruption Potential for negative publicity - avoidable with careful handling Complaint probable Legal action possible
| 3 | Significant | Activities disrupted Negative publicity unavoidable Complaint probable Legal action probable
| 4 | Major | Activities interrupted for significant time Major negative publicity unavoidable Major legal action expected
Likelihood score
| Score | Description | Example
| 1 | Unlikely | Not expected to occur within two years
| 2 | Possible | May occur within 12 to 24 months
| 3 | Likely | Could occur within 12 months
| 4 | Highly likely | Expected to occur within 12 months

## Risk register template
Risk register - Edit name of Group/District/County
Step 1: Identify the risks |  |  |  | Step 2: Assess the risks |  |  |  |  | Step 3: Control the risks |  |  |  | Step 4: Monitor the risks
[6 empty] | Pre-control |  |  |  | Post-control
ID | Date added | Category | Risk owner | Risk | Impact | Impact score | Likelihood score | Score | Current controls | Impact score | Likelihood score | Score | How will the risk be monitored | Further actions | By when | Responsible | Last review date
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
Note on B5: Number your risks to make it easier to find and refer to them
Note on C5: Date the risk is added to this register
Note on D5: Choose which type of risk you are recording from the drop down list
Note on E5: One person who is the named risk owner (you can use role titles)
Note on F5: A line or short sentence that describes the risk
Note on G5: A short sentence that describes what the impact would be if the risk happened
Note on H5: What's the impact before you have any measures or 'controls' in place? 1- Minor 2- Important 3- Significant 4- Major More information on the guidance tab
Note on I5: What's the likelihood before you put any measures or 'controls' in place? 1- Unlikely 2- Possible 3- Likely 4- Highly Likely More information on the guidance tab
Note on K5: This is where you record all the different measures or 'controls' you already have in place to reduce the impact or likelihood of the risk actually happening
Note on L5: What's the impact with the controls in place? 1- Minor 2- Important 3- Significant 4- Major More information on the guidance tab
Note on M5: What's the likeliood with the controls in place? 1- Unlikely 2- Possible 3- Likely 4- Highly Likely More information on the guidance tab
Note on N5: This is the score after the controls are in place - this is your 'real' level of risk
Note on O5: What would you like to see to make you feel confident this is under control? See the guidance section for further tips
Note on P5: Further actions needed to manage the risk - maybe longer term plans
Note on Q5: Add a date so that you can keep track if things are going off course
Note on R5: Who are the people responsible for making sure the controls are in place and further actions are completed
Note on S5: Date the risk was last reviewed

## Risk register example
Risk register example - 1st Scoutburgh Valley Scouts
Step 1: Identify the risks |  |  |  | Step 2: Assess the risks |  |  |  |  | Step 3: Control the risks |  |  |  | Step 4: Monitor the risks
[6 empty] | Pre-control |  |  |  | Post-control
ID | Date added | Category | Risk owner | Risk | Impact | Impact score | Likelihood score | Score | Current controls | Impact score | Likelihood score | Score | How will the risk be monitored | Further actions | By when | Responsible | Last review date
1 | 2023-11-28 | Governance | Chair (Jamal) | Trustees may not have the required skills to carry out their roles. | Possible regulatory breaches. | 3 | 3 | 12 | Skill requirements identified and maintained. | 2 | 2 | 6 | Discuss and agree actions at every Trustee Board meeting. | Audit skills and identify any gaps. Then, develop next steps. | 2024-03-01 | Treasurer (Kim) Trustee (Anil) | 2023-12-12
2 | 2023-10-14 | Operational | Lead Volunteer (David) | Local programme delivery may not meet the needs of our community. | We aren’t reaching or engaging groups in IMD 1-5 areas. | 3 | 3 | 12 | Review current outreach and engagament efforts to identify what can be done differently. Initiatives to support and provide opportunities for local young people such as, lottery funding. | 3 | 2 | 9 | Trustee Board will review status and progress at the next meeting, with an update from the District Lead Volunteer. | The District Lead Volunteer will work with the Growth and Communities team to create and put a development plan in place. Reach out to other Districts for ideas and successful practices to help inform development plan. | 2024-03-01 | District Lead Volunteer (Anders) Joe, Eric, Amy, Dawn, Dave, Bumika, Grace | 2023-12-12
3 | 2023-10-21 | Operational | Lead Volunteer (David) | Too few volunteers - the two Cub volunteers who are also helping with Beavers suddenly leave. | We won’t be able to run Cubs and the Beaver section will also be affected. | 3 | 2 | 9 | Group Lead Volunteer holds annual informal reviews with all volunteers. Review on-going learning and training requirements. Regular checks in with individuals to see how they're feeling, discuss what could be done to reduce their volunteering tasks, if needed, and to get as much notice as possible if they do wish to stop or reduce their volunteering. | 1 | 2 | 3 | Updates to be provided by Group Lead Volunteer to District Lead as and when necessary | Put together a recruitment plan. Identify anyone in the Group or the District that could be asked to stand-in. Make sure there is a parent rota in place in Beavers and Cubs. | 2024-03-01 | Group Lead Volunteer (Joe) Eric, Bumika, Grace | 2023-12-12
4 | 2023-11-01 | External | Treasurer (Kim) | Damage to the roof of the Scout meeting place due to high winds and rain, including possible falling debris. | Can't go ahead with sessions. | 4 | 3 | 16 | Risk assessment. Planned maintenance work. Young people currently meeting in a church hall. | 1 | 1 | 2 | Monitor progress and costs. | Check quotes and organise start dates for repairs. Keep parents/ carers informed of progress. | 2024-01-01 | Group Lead Volunteer (Joe) | 2023-12-12
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
Note on B5: Number your risks to make it easier to find and refer to them
Note on C5: Date the risk is added to this register
Note on D5: Choose which type of risk you are recording from the drop down list
Note on E5: One person who is the named risk owner (you can use role titles)
Note on F5: A line or short sentence that describes the risk
Note on G5: A short sentence that describes what the impact would be if the risk happened
Note on H5: What's the impact before you have any measures or 'controls' in place? 1- Minor 2- Important 3- Significant 4- Major More information on the guidance tab
Note on I5: What's the likelihood before you put any measures or 'controls' in place? 1- Unlikely 2- Possible 3- Likely 4- Highly Likely More information on the guidance tab
Note on K5: This is where you record all the different measures or 'controls' you have in place to reduce the impact or likelihood of the risk actually happening
Note on L5: What's the impact with the controls in place? 1- Minor 2- Important 3- Significant 4- Major More information on the guidance tab
Note on M5: What's the likeliood with the controls in place? 1- Unlikely 2- Possible 3- Likely 4- Highly Likely More information on the guidance tab
Note on N5: This is the score after the controls are in place - this is your 'real' level of risk
Note on O5: What would you like to see to make you feel confident this is under control? See the guidance section for further tips
Note on P5: Further actions needed to manage the risk - maybe longer term plans
Note on Q5: Add a date so that you can keep track if things are going off course
Note on R5: Who are the people responsible for making sure the controls are in place and further actions are completed
Note on S5: Date the risk was last reviewed

## Key (hidden)
| Impact | Likelihood
Risk categories | 1 | 1
External | 2 | 2
Operational | 3 | 3
Financial | 4 | 4
Legal and Regulatory
Governance
Data protection