Scouts

New Section Checklist

Starting a new Section is an exciting challenge and an amazing way to welcome more young people to Scouts.

Here you’ll find practical steps and a simple checklist to guide you through the process. Setting up a new Section will be different each time, so use the checklist as a flexible guide, rather than a rigid timetable.

You can find more detailed information for each step on the Scouts website.

Before starting

| Task | Assigned to: | Target date: | Completed? |
| --- | --- | --- | --- |
| Consider the need for opening a new Section and how it could benefit your community |  |  |  |
| Think about where you’d like to meet and potential meeting days and times |  |  |  |
| Talk about the idea with your Group Lead Volunteer and Trustees and get permission to open a new Section |  |  |  |
| Get a working group or volunteer team together |  |  |  |

Notes:

12 weeks before starting

| Task | Assigned to: | Target date: | Completed? |
| --- | --- | --- | --- |
| Find out the price and availability of possible meeting places and make a provisional booking |  |  |  |
| Decide on the day and time of your meeting |  |  |  |
| Register the Section on the membership system |  |  |  |
| Talk about finances with the Group Lead Volunteer and Trustee Board |  |  |  |
| Advertise volunteer opportunities and recruit volunteers |  |  |  |
| Talk about an adult rota with new members and set one up |  |  |  |
| Plan how to recruit young members for your Section |  |  |  |
| Complete criminal records checks |  |  |  |
| Add new volunteers to the membership system for recruitment checks |  |  |  |
| Look at the Growing Roots learning for yourself and the volunteer team |  |  |  |

Notes:

## Eight weeks to go

| Task | Assigned to: | Target date: | Completed? |
| --- | --- | --- | --- |
| Make sure you’ve completed all required online learning |  |  |  |
| Read key policies and relevant risk assessments |  |  |  |
| Decide how data for the Section will be collected and stored |  |  |  |
| Advertise and promote the new Section to attract new members |  |  |  |

Notes:

## Six weeks to go

| Task | Assigned to: | Target date: | Completed? |
| --- | --- | --- | --- |
| Check in on your recruitment |  |  |  |
| Plan the budget for your Section |  |  |  |
| Plan your fundraising |  |  |  |
| Book face-to-face training for volunteers, including First Response |  |  |  |

Notes:

## Four weeks to go

| Task | Assigned to: | Target date: | Completed? |
| --- | --- | --- | --- |
| Check in with your Group Lead Volunteer |  |  |  |
| Visit a Section at another Group |  |  |  |
| Look at support available for your Section |  |  |  |
| Reply to enquiries |  |  |  |
| Review data protection processes |  |  |  |
| Start planning for your first term |  |  |  |
| Complete risk assessments |  |  |  |
| Think about Equity, Diversity and Inclusion |  |  |  |

Notes:

## Two weeks to go

| Task | Assigned to: | Target date: | Completed? |
| --- | --- | --- | --- |
| Hold a welcome meeting with your volunteer team |  |  |  |
| Give roles and responsibilities to the team |  |  |  |
| Make sure everyone feels part of the team |  |  |  |

Notes:

## One week to go

| Task | Assigned to: | Target date: | Completed? |
| --- | --- | --- | --- |
| Prepare your resources |  |  |  |
| Check in with your volunteer team |  |  |  |
| Contact parents/carers with final information |  |  |  |

Notes:

## On the day of your first meeting

| Task | Assigned to: | Target date: | Completed? |
| --- | --- | --- | --- |
| Make sure you have full joining information and consent for the young people |  |  |  |
| Have fun! |  |  |  |

## After your first meeting

| Task | Assigned to: | Target date: | Completed? |
| --- | --- | --- | --- |
| Reflect on the first session and check the plans for the next session |  |  |  |
| Order Scout uniform for volunteers |  |  |  |
| Talk about plans for your Section with your Group Lead Volunteer |  |  |  |
| Explore learning and development opportunities |  |  |  |
| Congratulations, it’s time to celebrate! |  |  |  |

Notes: