## Slide 1
How we Manage Change at Scouts

## Slide 2
Our Change Framework
  A step-by-step process for making change happen

## Slide 3
Our Change Framework provides
4 step process
Checklist of things to consider ​
Tools to guide teams​ leading change
This has been designed to be applied locally

## Slide 4
4 steps of change
Understand
Plan
Deliver
Keep Going
‘we get why the change is needed but also what the barriers are’​
‘we have a plan to support people through the change’
‘we are responding to feedback and celebrating successes'
‘it becomes just what we do'

## Slide 5
Where we are: May 2022
At the moment we're very much in the Understand stage so these slides focus on this step
Some Counties have Transformation Leads appointed whilst others are still in the process – we’re bringing leads together on 23 June 2022.

## Slide 6
Understand
i. The Change Itself | Why ask this
Do we understand what the change is going to involve? | It's important to be clear on what is practically going to change for volunteers
Can we explain why it’s needed? | Volunteers are more likely to get on board if they know what the benefits are
What will things look and feel like once the change is completed? | Help volunteers visualise what will be better when the change is done – yes it might be bumpy getting there but it will be worth it
What will stay the same? | Remember the fundamentals of Scouting remain the same. We get together to give young people skills for life!
ii. Peoples Response | Why ask this
Who will the change impact in my area? | Changes coming down the road will affect volunteers differently depending role – it's helpful to map this out
What might people like about the change and what might they be worried about? | This will help give a sense of what key messages and support might be needed to get volunteers on board
What barriers might people face? | What are the practical challenges volunteers are going to face when trying to implement change – this could be training needs, confidence, vacancies etc.
Checklist

## Slide 7
      Supporting tool (coming soon)
Are you ready for change?
Map groups in your area who will be impacted by the change
Think about what awareness there is of the change in your area, how motivated volunteers are to make it successful, and whether people have the necessary skills to adopt change locally
This should give a good indication of the potential barriers volunteers will face
You are now ready to move to the Plan step!
Understand

## Slide 8
Hold on, there’s no need to plan yet!
You’ll have July – end of 2022 to plan, so we’ll share updated slides to help you through the next steps at the end of June

## Slide 9
To be successful
Remember all 4 steps​ of change should be applied but only move to the next step when you are ready
Always dedicate plenty of time to planning
Use County/Area/Region(Scot) Transformation Leads (who are supported by a HQ change team) and others for support​

## Slide 10
  Thank you