## Slide 1
Transformation Leads Call
16 January 2024

## Slide 2
  Craig Turpie, Deputy UK Chief Volunteer
  Andrew Sutherland, Deputy Programme Sponsor
  Jack Caine, UK Lead Volunteer for People
  Lara Burns, Chief Digital Officer
  Paul Fix, Project Sponsor, Volunteer Journey
  Lucy Burrows-Smith, Volunteering Executive
  Hamish Stout, UK People Team Member
  Gemma Norman, Rob Groves, Change Team
  Adam Ray, Communications Manager
Who's on the call?

## Slide 3
  Timeline update
  Open Forum
  Change Readiness
    Ensuring Readiness for Migration
    County & District Structures & Teams
    Accreditations
  Open Forum
  Next steps & close
What we’ll cover

## Slide 4
Timeline update

## Slide 5
Open Forum

## Slide 6
Change Readiness

## Slide 7
Predicted RAG at Go-Live
Overall RAG - Progress so far
Change Readiness Overview
Chart: 
| Green | Amber | Red | Grey
Total | 4 | 38 | 31 | 15
Nov 23
Chart: 
| Green | Amber | Red | Grey
Total | 24 | 42 | 7 | 15
Nov 23
Chart: 
| Green | Amber | Red | No Response
RAG Overall | 12 | 51 | 21 | 4
Jan 24
Chart: 
| Green | Amber | Red | No Response
Predicated RAG at go-live | 33 | 44 | 7 | 4
Jan 24

## Slide 8
Chart: 
| Trustee Boards operating with new purpose | Trustee Boards managing risks of change | Local support structure for changes | Local processes reviewed | Ready to add accreditations | Role Title conversations | Districts & Groups confirmed new structure | County confirmed new structure | Appointments Progress | Updating email addresses | Communcation | Change Plan
Green | 19 | 6 | 5 | 6 | 3 | 3 | 2 | 17 | 20 | 22 | 20 | 43
Amber | 32 | 13 | 30 | 26 | 33 | 22 | 20 | 44 | 46 | 39 | 14 | 22
Red | 18 | 50 | 34 | 37 | 33 | 44 | 47 | 8 | 3 | 8 | 35 | 4
Change Readiness Overview – Nov 23

## Slide 9
Change Readiness Overview – Jan 24
Chart: 
| Trustee Boards operating with new purpose | Trustee Boards managing risks of change | Local support structure for changes | Local processes reviewed | Ready to add accreditations | Role Title conversations | Districts & Groups confirmed new structure | County confirmed new structure | Appointments Progress | Updating email addresses | Communcation | Change Plan
Green | 22 | 12 | 10 | 11 | 4 | 13 | 3 | 27 | 29 | 37 | 30 | 58
Amber | 43 | 20 | 40 | 37 | 48 | 36 | 44 | 53 | 52 | 42 | 22 | 25
Red | 19 | 52 | 34 | 36 | 32 | 35 | 37 | 4 | 3 | 5 | 32 | 1

## Slide 10
Communicating Locally
Some areas haven’t yet spoken to their Districts and Groups
Local Engagement
Engagement at District and Group level is challenging
Building Teams
Understanding how to move from current role to new teams, role mapping, sub-teams
Trustee Board Purpose & Readiness
Getting Groups & Districts up to date with Trustee Board changes
  Key Themes

## Slide 11
  Tonight, we’ll focus on three key elements of the survey ….
Making sure everyone is ready for migration
County, District and Group structures
Accreditations
Note that focussing on these will also address the ‘role title conversations’ element of the survey.

## Slide 12
a) Making sure everyone is ready for migration

## Slide 13
Your key local challenges to manage are:
Volunteer personal details should match the volunteer’s expectations when they first log on, for example:
  Correct email addresses
  Accurate / no missing roles (note: both multiple variants and no variants; Group Sectional Assistants)
  Their learning records are not missing any items
  Their awards are correctly listed
Communications
  Making sure that everybody in your County knows what they need to know and do (and why)
  Making sure there is accurate communication – no invention of local rules
  Ensuring migration readiness

## Slide 14
  Ensuring everyone is ready to exploit our new ways of working
Making sure our new ways of working will be used / exploited
Examples of possible challenges:
  Members who are unwilling to change, so work around the new systems rather than using them to give them more Scouting time and/or less volunteering time
  People saying they do work in teams, but not actually embracing the new ways of team working
  Local processes not being adjusted to the new ways of working
  Training teams continuing unchanged (‘hiding’ in the Volunteering Development Team)
  AACs continuing unchanged (‘hiding’ in the Volunteering Development Team)
  Section Teams continuing unchanged in their operation
County-wide readiness
  The challenge is to be sure that everybody in every Group and District will be at ‘green’ for at least the “Important” parts of the readiness checklist

## Slide 15
b) County, District & Group Structures and Teams

## Slide 16
  Teams - core principles
Key action: Make sure that for each County, District, Group and team...
Programme is at the core of everything that we do
Each Lead Volunteer is clear that only the teams listed in the organisation diagrams & POR may exist. Teams (except Section Teams) may have sub-teams if appropriate to their operation.
Each team member understands the core principles of working in teams - see Volunteering Together and Our Volunteering Culture
Each team must meet their Team Description, but can organise themselves to achieve that, so that each team member is clear about their role in the team - see How volunteers work in teams

## Slide 17
  Key action: Creating clear understanding and effective leadership of each team by…
  Making sure each team (County, District and Group) has someone that leads the team (Team Leader, or Lead Volunteer for the Leadership Team, and Chair for Trustee Board)
  The people leading the team are clear about their role - facilitating the team so that they collectively achieve its purpose (from the team description)
  Volunteers leading a team will be:
    Creating a positive team environment
    Helping their team members to find what they need
    Attracting and welcoming new volunteers
    Reflecting and reviewing the team
  More detail at Leading a Team
  Team leadership

## Slide 18
Inclusion
It’s embedded in Our Volunteering Culture
Inclusion is built in, not bolt on
It's fundamental to everyone's role and team

## Slide 19
Inclusion in teams in practice
What are some likely ways in which this will work in practice?
Leadership Teams - if you, or the people leading inclusion where you volunteer, have a breadth of impact – supporting inclusion across volunteers, young people and programme, new provision, wider teams, etc.
Inclusion Team – sub-team of Leadership Team - if you've got a group of inclusion volunteers already or want to grow or focus in this way.
Specific teams - if you, or the people leading inclusion where you volunteer, have a more specific focus:
Programme Team. For example, doing parent carer frameworks, assisting with reasonable adjustment requests, advising on delivering inclusive camps.
Volunteering Development Team. For example, embedding inclusive practise through inductions, helping volunteers learn and share best practise around inclusion
Support Team. For example, looking after relationships with other organisations that support inclusive growth.
It’s flexible!

## Slide 20
Role titles will be clearer, more inclusive, and understandable to everyone
  Formally recorded on scouts.org.uk. For example, Team Member, Team Leader or Lead Volunteer
  Flexible about how you continue to describe yourself. For example, ‘I help make sure Scouts is inclusive and accessible for all’ or ‘I'm the Inclusion Lead’
Important to have conversations
  With inclusion volunteers about what team they'll be in
  With wider teams about how they'll embed inclusion
Inclusion - moving to our new approach

## Slide 21
  Actions: Local structures
Each County, District, and Group should aim to:
  Have discussions with all current (and new or potential) team members
  Appoint Team Leaders and Team Members for each of the teams (and any sub-teams where relevant)
  Allocate tasks within the team. Consider who will have accreditations relating to the team (these largely relate to County and District teams, but may be given to volunteers in Groups and Sections)
  Start to informally work in new team structures
  More detail on Becoming part of a new team | Scouts (and opportunity to join session on Tuesday 23rd January – see link in post-call email)

## Slide 22
c) Accreditations

## Slide 23
Why are accreditations introduced? What problem are we solving?
Rather than allocating tasks to a team, we sometimes need to allocate a task to one or more specific people
A key benefit of this is that some bite-sized tasks can be shared with people who have their primary role in another team, rather than them taking on the full responsibility of an additional team
They also benefit a team so that the team can focus on its core purpose
An important benefit is that some roles become more attractive and achievable, without distracting too much from the volunteer’s primary role
It also enables Lead Volunteers to share some responsibilities and draw on volunteers' expertise and experience in key areas, for example safeguarding.
  Accreditations

## Slide 24
  Accreditations - core principles
Accreditations are a way of sharing tasks and responsibilities, where a volunteer needs to be given certain permissions to take these on
Available accreditations are listed in the Accreditations Table in POR; no others can exist
Accreditations are not ‘roles’ - they're permission to do a specific task
Accreditations can only be given to volunteers who are already full members
Accreditations are usually given by the Team Leader of that team or a Lead Volunteer

## Slide 25
  Accreditations will reflect:
For some topics, the need to have a person with particular (usually specialised) skills
In other cases, the sharing of responsibilities so that one individual (e.g. a Lead Volunteer) does not get overloaded
Or, the need for UKHQ to know who to contact to about a particular topic (for example who to send Awards to within a County or District)
  Accreditations are not a team membership
  An accreditation does not create a membership of a specific team. However, the task is affiliated to a team.
  For example, a Cub Section Team Member who is an excellent kayaker could have an appropriate “Kayak Assessor” accreditation. They would be affiliated to, but not be a member of, the County Programme Team.
  Key facts about accreditations

## Slide 26
  The Accreditations Table
Most accreditations have pre-requisite(s) that must be verified before the accreditation can be given
The accreditations table shows, for each accreditation:
  Accreditation title
  The team responsible for the accreditation (creating, where necessary, an informal network of affiliated people who have that accreditation)
  Who (role) can give or remove the accreditation
  About the person who can hold the accreditation
    whether they are in a role that undertakes regulated activity
    what learning must the person have already completed, and what other qualifications must already be held
    if an internal check is needed for the accreditation
  Maximum time that the accreditation can be held for before review
  If no accreditation is given, who do the related responsibilities and tasks sit with by default

## Slide 27
  Useful resources - accreditations
Accreditations | Scouts
Leadership Team Accreditations | Scouts
Programme Team Accreditations | Scouts
Volunteering Development Team Accreditations | Scouts
UKHQ Accreditations | Scouts

## Slide 28
  Useful resources - teams
Tools to support Volunteering Development Teams | Scouts
  Questions to help you reflect on how you volunteer together include:
  Doing tasks as one team
  Sharing and coordinating accreditations
  Collaborating with other teams

## Slide 29
Open Forum

## Slide 30
Next Steps

## Slide 31
Look at how you can build inclusivity into your Teams, Sub-teams and local processes
Continue working on County, District & Group Team Structures
Look out for invites to support with some new web resources and layout
Watch and share the Welcome Workshop recording within your County
Explore and share the new Welcome & Learning webpages
What you can do:
  Re-planning POR release date
  Working to provide an updated timeline as soon as possible
  Updating page design and resources for role mapping
  Planning out upcoming webinars focussing on specific teams
  Sharing our updated Trustee resources including:
    Trustee Board Annual Planner
    Risk Register Webpage
    Appointing Trustees Guidance
What we’re doing:

## Slide 32
Thank You